## Axis 1
Priority Axis | IP | Actions | Indicative allocation at action level in adopted OP (total cost, euro) | Revised indicative allocation at action level proposed (total cost, euro) | % Change | PF? | Output indicators (per action) | Indicative allocation at indicator level in adopted OP (total cost, euro) | Revised indicative allocation at indicator level proposed (total cost, euro) | % change | 2023 indicator target at action level in adopted OP | Revised 2023 indicator target at action level | % Change | GU's explanation for the revision of targets for output indicators. Incorrect assumptions motivating the change should be duly explained. For example, if the target adjustment is due to a change in unit costs, the unit costs used for the calculation of targets in columns L and M should be provided. | Desk agrees with the change proposed? (Yes, No)
PA 1 | 7(i) | Construction, modernisation, rehabilitation, electrification and establishment of signalling and telecommunication systems of railway sections on the "core" and "comprehensive" Trans-European Transport Network | 712944722 | 513945910 | -27.91% |  | CO12a Total length of reconstructed or upgraded railway line, of which: TEN-T | 712944722 | 513945910 | -27.91% | 111 | 33 | -70.27% | The target value of the indicator was defined on the basis of the planed projects not on the basis of the funds available. The necessary budjet for implementation of the projects significantly exceeds the initially allocated funds under PA 1. The newly defined target value of the indicator takes into account the target value for the Plovdiv-Burgas railway line project, which, although it will not be fully completed and functional in its entirety by the end of 2023, will still have sections completed and put into operation. Sections of the Elin Pelin - Kostenets modernization project and the Voluyak - Dragoman section modernization project will be completed and operational by the end of 2025. Funds under PA 1 of OPTTI will be used for Phase 1 / Stage 1 of the projects but the initially planned target value of the indicator will be achieved in full upon completion of the projects in the new program period. The projects will not be fully completed in the current programming period and the target value of the indicator will not be achieved as initially planned due to significant change in the economic, environmental and labour market conditions. The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies.
| 7(i) | Construction, modernisation, rehabilitation, electrification and establishment of signalling and telecommunication systems of railway sections on the "core" and "comprehensive" Trans-European Transport Network | 712944722 | 513945910 | -27.91% |  | Removed railway crossings in the modernized railway sections | 712944722 | 513945910 | -27.91% | 43 | 15 | -65.12% | The target value of the indicator was defined on the basis of the planed projects not on the basis of the funds available.The newly defined target value of the indicator takes into account Stage 1 of "Plovdiv - Burgas, Phase 2" - 11 pieces, "Septemvri - Plovdiv: part of the Trans-European railway network - construction of four road overpasses" - 4 pieces. After the entire completion, the level crossings removed will be 43. The "Plovdiv - Burgas, Phase 2" project will not be fully completed in the current programming period and the target value of the indicator will not be achieved as initially planned due to significant change in the economic, environmental and labour market conditions. The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies.
| 7(i) | Construction, modernisation, rehabilitation, electrification and establishment of signalling and telecommunication systems of railway sections on the "core" and "comprehensive" Trans-European Transport Network | 712944722 | 513945910 | -27.91% |  | Overpasses and underpasses built along the modernized railway sections | 712944722 | 513945910 | -27.91% | 42 | 15 | -64.29% | The target value of the indicator was defined on the basis of the following projects: Plovdiv - Burgas" - 11 structures, "Modernization of the railway section Septemvri - Plovdiv: part of the Trans-European railway network - construction of four road overpasses" - 4 structures.The "Plovdiv - Burgas, Phase 2" project will not be fully completed in the current programming period and the target value of the indicator will not be achieved as initially planned due to significant change in the economic, environmental and labour market conditions. The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies.
| 7(i) | Development of multimodal urban rail to improve connectivity and accessibility on the Trans-European Transport Network | 0 | 70588235 | 100% |  | Metro lines under design | 0 | 70588235 | 100% | 0 | 5.6 | 100% | Newly defined indicator - It represents the total length of the metro lines that will be in the process of working design and preparation. The value of the indicator is obtained by summing the kilometers of metro lines for which at least one contract for work design has been concluded as of the date of the report.
[7 empty] | Metro trains under design | 0 | 70588235 | 100% | 0 | 16 | 100% | Newly defined indicator - It represents the total number of metro trains that will be in the design process. The value of the indicator is obtained on the basis of the number of metro trains for which a contract for production and delivery has been concluded as of the date of the report.
Total Axis |  |  | 712944722 | 584534145 | -18.01% | [7 empty] | 0.3277%
Output indicators in Performance Framework | [6 empty] | CO12a Total length of reconstructed or upgraded railway line, of which: TEN-T | 712944721 | 584534145 | 0.18011 | 111 | 33 | -0.7027 | The target value of the indicator was defined on the basis of the planed projects not on the basis of the funds available. The necessary budjet for implementation of the projects significantly exceeds the initially allocated funds under PA 1. The newly defined target value of the indicator takes into account the target value for the Plovdiv-Burgas railway line project, which, although it will not be fully completed and functional in its entirety by the end of 2023, will still have sections completed and put into operation. Sections of the Elin Pelin - Kostenets modernization project and the Voluyak - Dragoman section modernization project will be completed and operational by the end of 2025. Funds under PA 1 of OPTTI will be used for Phase 1 / Stage 1 of the projects but the initially planned target value of the indicator will be achieved in full upon completion of the projects in the new program period. The projects will not be fully completed in the current programming period and the target value of the indicator will not be achieved as initially planned due to significant change in the economic, environmental and labour market conditions. The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies.
[7 empty] | Certified expenditures | 712944721 | 584534145 | 0.18011 | 712944722 | 500000000 | -0.29868 | The change is due to the reduction of the scope of phase 1 of the projects under PA 1
[7 empty] | Number of major projects with started construction | 712944721 | 584534145 | 0.18011 | 3 | 3 | 0 | No change - the number of major projects with started construction remains the same. The entire completion of the projects will be in programming period 2021-2027.
NOTE: Data on allocations should be provided either at action level (columns D,E) or at indicator level (columns I,J), depending on availability

## Axis 2
Priority Axis | IP | Actions | Indicative allocation at action level in adopted OP (total cost, euro) | Revised indicative allocation at action level proposed (total cost, euro) | % Change | PF? | Output indicators (per action) | Indicative allocation at indicator level in adopted OP (total cost, euro) | Revised indicative allocation at indicator level proposed (total cost, euro) | % change | 2023 indicator target at action level in adopted OP | Revised 2023 indicator target at action level | % Change | GU's explanation for the revision of targets for output indicators. Incorrect assumptions motivating the change should be duly explained. For example, if the target adjustment is due to a change in unit costs, the unit costs used for the calculation of targets in columns L and M should be provided. | Desk agrees with the change proposed? (Yes, No)
PA 2 | 7(i) | TEN-T motorways and roads – core network (new construction) | 560165085 | 503516887 | -10.11% |  | CO13a Total length of newly built roads, of which: TEN-T | 560165085 | 503516887 | -10.11% | 79.553 | 65.9 | -17.16% | For the target value of the indicator, the following projects included in the program are taken into account: Lot 3.1 Blagoevgrad - Krupnik - (9.7 km) on the "Struma" Motorway, which includes the implementation of two sections: - section 1 from km 359+000 to km 366+000 /7 km/ - section 2 from km 370+400 to km 373+100 /2.7 km/ Lot 3.1 - "Zheleznitsa" tunnel on "Struma" Motorway - section from km 366+000 to km 370+400 (4.4 km) Lot 3.3 Kresna - Sandanski on "Struma" Motorway from km 397+000 to km 420+624 (23.624 km). "Kalotina - Sofia" Motorway, Lot 1, Western arc of the Sofia ring road, phase 2, section from km 0+780 to km 6+308.17, with a total length of 5.528 km. "Europa" Motorway from km 15+500 to km 48+903. From this section will be executed: - the section of "Europa" Motorway from km 15+500 to km 32+447.20 was built with national funds and has been put into operation since 2020 - 16.95 km; - section from km 32+447.20 to km 48+903– 16.45 km.The construction is in progress, but the section will not be completed in its entirety within the period of eligibility of costs under OPTTI. It is planned to build 5.7 km of the route. The overall completion of Struma Motorway is planned for the programming period 2021-2027. The project is included in the scope of the "Transport Connectivity" Programme 2021-2027. On the recommendation of the European Commission, the financing of the section from km 373+100 to km 376+000, falling into Lot 3.1 Blagoevgrad - Krupnik, was excluded from the Application Form for financing the "Struma" Motorway project Lot 3.1, Lot 3.3 and the "Zheleznitsa" tunnel. The reason for excluding the financing of the section is that at the time when the Application Form was approved by the EC, the EIA procedure of Lot 3.2 had been started, but the final decision on the EIA of the Minister of Environment and Water had not yet been made, and that the construction of these 2.9 km is organizationally and technically related to the construction of Lot 3.2, but is a contractual obligation of the Contractor of Lot 3.1.The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies.
| 7(i) | Secondary road links to TEN-T road network and nodes (new build) | 0 | 45058774 | 100% |  | Length of newly built road links to TEN-T | 0 | 45058774 | 100% | 0 | 4.68 | 100% | For the target value of the indicator "Length of built road connections to TEN-T", the project for the construction of the Bypass of the city of Burgas from km 230+700 on the road I-9 Sarafovo - Burgas to km 493+550 on the road I-6 Vetren-Burgas and local lanes is taken into account. The length of the road section as a connection between two sections of the TEN-T is 4.68 km.
Total Axis |  |  | 560165085 | 548575661 | -2.069% | [7 empty] | 82.84%
Output indicators in Performance Framework | [6 empty] | CO13a Total length of newly built roads, of which: TEN-T | 560165085 | 503516887 | 0.10113 | 79.553 | 65.9 | -0.17162 | For the target value of the indicator, the following projects included in the program are taken into account: Lot 3.1 Blagoevgrad - Krupnik - (9.7 km) on the "Struma" Motorway, which includes the implementation of two sections: - section 1 from km 359+000 to km 366+000 /7 km/ - section 2 from km 370+400 to km 373+100 /2.7 km/ Lot 3.1 - "Zheleznitsa" tunnel on "Struma" Motorway - section from km 366+000 to km 370+400 (4.4 km) Lot 3.3 Kresna - Sandanski on "Struma" Motorway from km 397+000 to km 420+624 (23.624 km). "Kalotina - Sofia" Motorway, Lot 1, Western arc of the Sofia ring road, phase 2, section from km 0+780 to km 6+308.17, with a total length of 5.528 km. "Europa" Motorway from km 15+500 to km 48+903. From this section will be executed: - the section of "Europa" Motorway from km 15+500 to km 32+447.20 was built with national funds and has been put into operation since 2020 - 16.95 km; - section from km 32+447.20 to km 48+903– 16.45 km.The construction is in progress, but the section will not be completed in its entirety within the period of eligibility of costs under OPTTI. It is planned to build 5.7 km of the route. The overall completion of Struma Motorway is planned for the programming period 2021-2027. The project is included in the scope of the "Transport Connectivity" Programme 2021-2027. On the recommendation of the European Commission, the financing of the section from km 373+100 to km 376+000, falling into Lot 3.1 Blagoevgrad - Krupnik, was excluded from the Application Form for financing the "Struma" Motorway project Lot 3.1, Lot 3.3 and the "Zheleznitsa" tunnel. The reason for excluding the financing of the section is that at the time when the Application Form was approved by the EC, the EIA procedure of Lot 3.2 had been started, but the final decision on the EIA of the Minister of Environment and Water had not yet been made, and that the construction of these 2.9 km is organizationally and technically related to the construction of Lot 3.2, but is a contractual obligation of the Contractor of Lot 3.1.The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies.
[7 empty] | Certified expenditure | 560165085 | 548000000 | 0.021717 | 560165085 | 560165085 | 0 | Minor change in relation to the funds available, the number of major projects remains the same. Additional project was included in order to absorb the funds available.
[7 empty] | Number of major projects with started construction | 560165085 | 548575661 | 0.020689 | 3 | 3 | 0 | No change - the number of major projects with started construction remains the same. The entire completion of the projects will be in programming period 2021-2027.

## Axis 3
Priority Axis | IP | Actions | Indicative allocation at action level in adopted OP (total cost, euro) | Revised indicative allocation at action level proposed (total cost, euro) | % Change | PF? | Output indicators (per action) | Indicative allocation at indicator level in adopted OP (total cost, euro) | Revised indicative allocation at indicator level proposed (total cost, euro) | % change | 2023 indicator target at action level in adopted OP | Revised 2023 indicator target at action level | % Change | GU's explanation for the revision of targets for output indicators. Incorrect assumptions motivating the change should be duly explained. For example, if the target adjustment is due to a change in unit costs, the unit costs used for the calculation of targets in columns L and M should be provided. | Desk agrees with the change proposed? (Yes, No)
PA 3 | 4e | Clean urban transport infrastructure and promotion (including equipment and rolling stock) - Sofia metro projects | 409213372 | 406062690 | -0.7699% |  | CO15 Total length of new or improved tram and metro lines | 409213372 | 406062690 | -0.7699% | 12 | 13.1 | 9.167% | The target value of the indicator Total length of new or improved tram and metro lines has been changed to 13.1 km. The initially set target value did not include phase 2 of the Sofia Metro Line 2 Extension Project, section Metro station "James Boucher" to Metro station "Vitosha" - phase 2, which was financed by OPTTI and was put into operation in 2016. The section is 1.1 km long.
| 4e | Clean urban transport infrastructure and promotion (including equipment and rolling stock) - Sofia metro projects | 409213372 | 406062690 | -0.7699% |  | New metro stations | 409213372 | 406062690 | -0.7699% | 12 | 13 | 8.333% | The target value of the indicator New metro stations has been changed to 13. The initially set target value did not include phase 2 of the Sofia Metro Line 2 Extension Project, section Metro station "James Boucher" to Metro station "Vitosha" - phase 2, which was financed by OPTTI and was put into operation in 2016. The section has 1 metro station.
| 4e | Clean urban transport infrastructure and promotion (including equipment and rolling stock) - Sofia metro projects | 409213372 | 406062690 | -0.7699% |  | Depot | 409213372 | 406062689 | -0.7699% | 1 | 1 | 0% | The indicator remains the same.
| 4e | Clean urban transport infrastructure and promotion (including equipment and rolling stock) - Sofia metro projects | 409213372 | 406062690 | -0.7699% |  | Metro trains | 409213372 | 406062689 | -0.7759% | 20 | 20 | 0% | The indicator remains the same.
| 7a | Multimodal transport (TEN-T) - railway stations | 14406248 | 13229778 | -8.166% |  | Reconstructed railway stations | 14406248 | 13229778 | -8.893% | 6 | 5 | -20% | Number of stations that will be reconstructed according to PO 3 of OPTTI: 5 – Poduene, Iskar, Kazichene; Karnobat and Stara Zagora. The Nova Zagora station will not be completed within the period of eligibility of the costs, therefore it is not calculated in the reported value of the indicator.The project will not be fully completed in the current programming period and the target value of the indicator will not be achieved as initially planned due to significant change in the economic, environmental and labour market conditions. The Covid 19 pandemic posed challenges to the construction industry - delay with construction contracts deadlines, financial losses, staff retention. The war in Ukraine, sanctions and restrictions contributed to a spike in the price of construction materials and delays in supplies. The completion of the project is planned under PTC 2021-2027.
|  |  | 423619620 | 419292468 | -1.021% | [7 empty] | -2.5%
Output indicators in Performance Framework | [6 empty] | Certified expenditure | 423619620 | 420468938 | 0.0074375 | 423619620 | 400000000 | -0.055757 | Having in mind the reduction of funds and the uncеrtanity in the economic, environmental and labour market conditions.
[7 empty] | Number of major projects with started construction | 409213372 | 406062690 | 0.0076994 | 1 | 2 | 1 | The already completed major projects are the following: - Sofia metro extension project: Line 3, Stage I – section “Vladimir Vazov Blvd. – Centre – Zhitnitsa Str.” - Sofia metro extension project: Line 3, Stage II – section “Zhitnica” str. – “Ovcha Kupel” R.A. – Sofia ring road”
[7 empty] | CO15 Total length of new or modernized tram and metro lines | 409213372 | 406062690 | 0.0076994 | 12 | 13.1 | 0.091667 | The target value of the indicator "Total length of new or improved tram and metro lines" has been changed to 13.1 km. The initially set target value did not include phase 2 of the Sofia Metro Line 2 Extension Project, section Metro station "James Boucher" to Metro station "Vitosha" - phase 2, which was financed by OPTTI and was put into operation in 2016. The section is 1.1 km long.

## Axis 4
Priority Axis | IP | Actions | Indicative allocation at action level in adopted OP (total cost, euro) | Revised indicative allocation at action level proposed (total cost, euro) | % Change | PF? | Output indicators (per action) | Indicative allocation at indicator level in adopted OP (total cost, euro) | Revised indicative allocation at indicator level proposed (total cost, euro) | % change | 2023 indicator target at action level in adopted OP | Revised 2023 indicator target at action level | % Change | GU's explanation for the revision of targets for output indicators. Incorrect assumptions motivating the change should be duly explained. For example, if the target adjustment is due to a change in unit costs, the unit costs used for the calculation of targets in columns L and M should be provided. | Desk agrees with the change proposed? (Yes, No)
PA 4 | 7(c) | Intelligent transport systems | 14606157 | 14322189 | -1.944% |  | Introduced/ upgraded navigation information systems | 14606157 | 14322189 | -1.944% | 1 | 2 | 100% | The output indicator “Introduced/ upgraded navigation information systems” has been updated in relation to the following projects: - "Territorial expansion of the scope and complement of the functions of the Vessel Traffic Management Information System (VTMIS) - Phase 4"; - "Delivery, installation and commissioning of port reception facilities (PPS) in Bulgarian ports for public transport of national importance".
| 7(c) | Inland waterway and ports | 13691980 | 12605556 | -7.935% |  | Delivered of multipurpose vessels | 13691980 | 12605556 | -7.935% | 3 | 5 | 66.67% | The output indicator "Delivered of multipurpose vessels" has been updated in relation to the completed activities on the projects for: "Improvement of the navigation systems and topo-hydrographic measurements on the Danube River - phase 2" and "Modernization and optimization of the rehabilitation activities of the shipping route in the common Bulgarian - Romanian section of the Danube River, through the supply of equipment”. As part of the first project, in 2017, the hydrographic vessel Danube 1 was built. Within the framework of the second project, the following were built/delivered: dredging equipment (group), which consists of a dredger, a pontoon, a barge, which are non-self-propelled vessels, and a shunting vessel (pipes are also included within the equipment).
| 7(c) | Seaports (TEN-T) | 7270383 | 20556350 | 182.7% |  | Commissioned port reception facilities for ship-generated waste | 7270383 | 20556350 | 182.7% | 2 | 7 | 250% | The output indicator "Commissioned port reception facilities for ship-generated waste" has been updated in relation to the actually performed activities within the project "Delivery, installation and commissioning of port reception facilities (PRF) in the Bulgarian ports for public transport of national importance". Within the framework of the project under PA 5 "Technical assistance for the preparation and implementation of the project "Delivery, installation and commissioning of port reception facilities (PRF) in the Bulgarian ports for public transport of national importance", preliminary design studies were carried out. As a result of the analysis, a prioritized list for PRFs was provided, which was agreed with the beneficiary and was used in the preparation of the task and the documentation for the public procurement for the investment project under OPTTI. Accordingly to the prioritized lists presented and accepted by the beneficiary, 5 sets of containers and racks for separate collection of waste resulting from shipping activity according to the recommendations of the Danube Convention (for the river) and types of waste for the sea according to MARPOL, Annex I, Annex V, as well as a set of equipment for prevention and response to operational and emergency pollution - 2 pieces containing - bollards and those for their deployment, skimmers intended for the collection of various types of petroleum products and oils, collectors for the collection of solid waste from the water surface, auxiliary equipment, high-speed boats equipped for transport, equipment and operation, as well as with reception capabilities of solid waste from ships.
| 7(c) | Clean urban transport infrastructure and promotion (including equipment and rolling stock) | 9158261 | 8393368 | -8.352% |  | Metro stations equipped with platform screen doors | 9158261 | 8393368 | -8.352% | 2 | 12 | 500% | The target value of the indicator Metro stations equipped with platform screen doors should be 12. The initial target value of 2 metro stations was set in connection with the specifics of the contract for the implementation of the project for the design, supply, installation and commissioning of Automatic platform screen doors (APSD) with a vertical opening for 12 metro stations from Line 1 of the metro in Sofia, which provided for the initial commissioning of the APSD of 2 metro stations, then, depending on the results, the implementation of the APSD of the remaining 10 metro stations. As of 30.10.2022, the project has been completed and the APSD of the 12 metro stations provided for in the project have been put into operation.
| 7(c) | Intelligent transport systems | 14606157 | 14322189 | -1.944% |  | Introduced train management system | 14606157 | 14322189 | -1.944% | 1 | 1 | 0% | The indicator remains the same.
|  |  | 44726781 | 55877463 | 24.93% | [7 empty] | 816.7%
Output indicators in Performance Framework | [6 empty] | Certified expenditure | 44726781 | 55877463 | -0.24931 | 44726781 | 44726781 | 0 | The indicator remains the same.
[7 empty] | Implemented/ modernized transport systems | 44726781 | 55877463 | -0.24931 | 3 | 3 | 0 | The indicator remains the same.
[7 empty] | Number of contracts with started construction | 44726781 | 55877463 | -0.24931 | 1 | 1 | 0 | The indicator remains the same.

## Axis 5
Priority Axis | IP | Actions | Indicative allocation at action level in adopted OP (total cost, euro) | Revised indicative allocation at action level proposed (total cost, euro) | % Change | PF? | Output indicators (per action) | Indicative allocation at indicator level in adopted OP (total cost, euro) | Revised indicative allocation at indicator level proposed (total cost, euro) | % change | 2023 indicator target at action level in adopted OP | Revised 2023 indicator target at action level | % Change | GU's explanation for the revision of targets for output indicators. Incorrect assumptions motivating the change should be duly explained. For example, if the target adjustment is due to a change in unit costs, the unit costs used for the calculation of targets in columns L and M should be provided. | Desk agrees with the change proposed? (Yes, No)
PA 5 | TA | Preparation, implementation, monitoring and inspection | 19907941 | 34047290 | 71.02% |  | Number of trainings of employees of Managing Authority and beneficiaries | 19907941 | 34047290 | 71.02% | 1000 | 1000 | 0% | The indicator remains the same.
| TA | Evaluation and studies | 25375961 | 3844835 | -84.85% |  | Adopted communication Strategy | 25375961 | 3844835 | -84.85% | 1 | 1 | 0% | The indicator remains the same.
| TA | Evaluation and studies | 25375961 | 3844835 | -84.85% |  | Adopted Evaluation plan | 25375961 | 3844835 | -84.85% | 1 | 1 | 0% | The indicator remains the same.
| TA | Preparation, implementation, monitoring and inspection | 19907941 | 34047290 | 71.02% |  | Meetings held of the MC | 19907941 | 34047290 | 71.02% | 16 | 16 | 0% | The indicator remains the same.
| TA | Preparation, implementation, monitoring and inspection | 19907941 | 34047290 | 71.02% |  | Number of employees (Full-time equivalents, FTEs) whose salaries are co-financed by technical assistance | 19907941 | 34047290 | 71.02% | 45 | 45 | 0% | The indicator remains the same.
| TA | Information and communication | 2383529 | 1775306 | -25.52% |  | Major information activities | 2383529 | 1775306 | -25.52% | 8 | 8 | 0% | The indicator remains the same.
| TA | Information and communication | 2383529 | 1775306 | -25.52% |  | Number of public information events | 2383529 | 1775306 | -25.52% | 20 | 10 | -50% | The target value of the indicator will not be achieved as initially planned due to significant change in the economic, environmental and labour market conditions.The pandemic of COVID 19 in 2020 and 2021 and the drastic restrictive measures taken to reduce the spread of the virus, led to the impossibility of holding various public events. Due to which the initially pledged 20 public events for OPTTI will not be realized until the end of 2023. In this regard, the indicator was updated to 10 public events.
| TA | Preparation, implementation, monitoring and inspection | 19907941 | 34047290 | 71.02% |  | Number of on the spot checks | 19907941 | 34047290 | 71.02% | 120 | 120 | 0% | The indicator remains the same.
|  |  | 47667431 | 39667431 | -16.78% | [7 empty] | -50%

## Axis 6
Priority Axis | IP | Actions | Indicative allocation at action level in adopted OP (total cost, euro) | Revised indicative allocation at action level proposed (total cost, euro) | % Change | PF? | Output indicators (per action) | Indicative allocation at indicator level in adopted OP (total cost, euro) | Revised indicative allocation at indicator level proposed (total cost, euro) | % change | 2023 indicator target at action level in adopted OP | Revised 2023 indicator target at action level | % Change | GU's explanation for the revision of targets for output indicators. Incorrect assumptions motivating the change should be duly explained. For example, if the target adjustment is due to a change in unit costs, the unit costs used for the calculation of targets in columns L and M should be provided. | Desk agrees with the change proposed? (Yes, No)
PA 6 | 3 (d) | production investments in small and medium-sized enterprises ERDF | 0 | 1000000 | 100% |  | CO01 Number of enterprises receiving support | 0 | 1000000 | 100% | 0
| 3 (d) | production investments in small and medium-sized enterprises ERDF | 0 | 1000000 | 100% |  | CO02 Number of enterprises receiving grants | 0 | 1000000 | 100% | 0
| 3 (d) | production investments in small and medium-sized enterprises CF | 0 | 119000000 | 100% |  | CO01 Number of enterprises receiving support | 0 | 119000000 | 100% | 0
| 3 (d) | production investments in small and medium-sized enterprises CF | 0 | 119000000 | 100% |  | CO02 Number of enterprises receiving grants | 0 | 119000000 | 100% | 0
|  |  | 0 | 120000000 | 100% | [7 empty] | 0%
Output indicators in Performance Framework | [6 empty] | NA | NA | NA | NA | NA | NA | NA
[7 empty] | NA | NA | NA | NA | NA | NA | NA
[7 empty] | NA | NA | NA | NA | NA | NA | NA