**P-United Ltd.**

**FINAL REPORT**

**on the implementation of public procurement:**

**„Providing consulting assistance for conducting an independent Strategic Environmental Assessment for the purpose of programming the Maritime, Fisheries and Aquaculture Programme 2021-2027“**

**Contracting Authority: Ministry of Agriculture**

**Contractor: P-United Ltd.**

**June, 2022**

**Sofia**

**CONTRACT IDENTIFICATION**

|  |  |
| --- | --- |
| **Name of the public procurement:** | **Providing consulting assistance for conducting an independent Strategic Environmental Assessment for the purpose of programming the Maritime, Fisheries and Aquaculture Programme 2021-2027** |
| **Contracting Authority:** | **Ministry of Agriculture** |
| **Contractor:** | **P-United Ltd.** |
| **Contract №:** | **РД 51-67/28.06.2021** |
| **Date of the contract signature:** | **28.06.2021** |
| **Deadline** | **22.07.2022** |
| **Kind of Report:** | **Final Report** |
| **Date of the Report:** | **14.06.2022** |
| **Manager** | **Assoc. Prof. Petar Petrov, PhD** |
| **Sign:** |  |

Table of Content:

[1. Introduction 4](#_Toc104892006)

[2. Analysis on the results and the achievements within the implementation of the contract 7](#_Toc104892007)

[2.1. Analysis of the results and the achievements within the implementation of Activity 1: „*Preparation of the necessary documents for notification, assessment of the need and scope for the SEA assessment and the Appropriate Assessment by the relevant Competent Authorities*“ from theContract 7](#_Toc104892008)

[2.2. Analysis of the results and the achievements within the implementation of Activity 2: „*Preparation of draft on the SEA Report in accordance with the requirements of Art. 16 and Art. 17 form the SEA Ordinance, incl. Appropriate Assessment (if such had been required by the Competent Authority)*“ from the Contract 8](#_Toc104892009)

[2.3. Analysis of the results and the achievements within the implementation of Activity 3: „*Assistance to the Contracting Authority in conducting consultations with the public, interested bodies and third parties who may be affected by the plan or program, in accordance with the requirements of Chapter Four of the SEA Ordinance*“ from the Contract 9](#_Toc104892010)

[2.4. Analysis of the results and the achievements within the implementation of Activity 4: „Preparation of final version of the SEA Report“ from the Contract 11](#_Toc104892011)

[3. In-depth analysis of the problems and recommendations for their solution in the future 12](#_Toc104892012)

[4. Deviations and/ or problems during the current reporting period 14](#_Toc104892013)

[5. Main Achievements 15](#_Toc104892014)

[6. Deliverables in accordance with the Technical specification 15](#_Toc104892015)

# Introduction

The current Final Report was developed within the frame of Contract РД 51-67/28.06.2021, which was signed between the Ministry of Agriculture and P-United Ltd. for the implementation of public procurement with subject: *„Providing consulting assistance for conducting an independent Strategic Environmental Assessment for the purpose of programming the Maritime, Fisheries and Aquaculture Programme 2021-2027“.*

The Managing Authority (MA) of the Maritime, Fisheries and Aquaculture Programme (MFAP) will use the the European Maritime, Fisheries and Aquaculture Fund (EMFAF) to provide support to meet the main challenges to the Fisheries sector during the programming period 2021-2027

The main challenges are closely related to the specifics of the Black Sea basin and the natural, social and economic situation in the Republic of Bulgaria.

The programming of the period 2021-2027 is taking place in a global pandemic caused by the spread of the COVID-19 virus, and its expected impact on the overall development of the country is still unclear due to the dynamics of the crisis nationally and globally. The COVID-19 crisis has had a significant social impact and is having a serious impact on economies and businesses in all areas.

Areas of MFAP support are a direct response to the EC Communication on the European Green Pact. The Communication aims to transform the EU into a society with a modern and resource-efficient, responsible economy with zero net emissions by 2050, through a strategy for a "Fair Transition" to a low-carbon economy.

In this way, the MFAP will contribute to the implementation of important European strategic documents such as the Green Pact, Farm to Table strategies, Blue Growth and the Biodiversity Strategy. In the programming period 2021-2027, the MFAP will implement two of the objectives of the EC's policy (PO) - PO2 "A greener, low-carbon Europe by promoting a clean and fair energy transition, green and blue investments, a circular economy, adaptation to Climate change and risk prevention and management "and PO 5" Europe closer to the citizen by promoting sustainable and integrated development of urban, rural and coastal areas and local initiatives ".

To meet these policy objectives, the MA will provide support on all EMFAF priorities.

The implementation of Priority 1 "Promoting sustainable fisheries and conservation of aquatic biological resources" must ensure that fishing activities are environmentally sustainable in the long run and managed in a way that is consistent with the objectives of economic, social and employment benefits. as well as for its contribution to food supply. The challenges for this priority are based on the Analysis of the Regional Sea Basin, the Situational Analysis of the State of the Fisheries Sector in Bulgaria, the Annual Report on the Fishing Fleet from 2020 and other documents.

The implementation of Priority 2 "Promoting sustainable aquaculture activities and the processing and marketing of fishery and aquaculture products" after 2020 aims to improve the link between funding and policy objectives, sustainable aquaculture growth, protection and improving the environment and natural resources by minimizing the negative impact on them. The main challenge under the Priority is the low competitiveness of enterprises and the sustainability of the sector. A more strategic approach is needed to increase the competitiveness of aquaculture, increase production and better address the specific challenges facing the sector.

The implementation of Priority 3 "Creating the conditions for the growth of a sustainable blue economy and stimulating the development of fisheries and aquaculture communities in coastal and inland areas" includes interventions that contribute to the development of fisheries and aquaculture communities , in coastal and inland areas. Through partnerships between stakeholders and specially designed management frameworks, solutions will be found to some of the main problems and challenges related to fishing pressure on stocks and the need for effective conservation measures, low profitability in fisheries areas, advanced working age strength and aging of the population, increasing the social acceptability of fish farming, keeping young people in fisheries areas and tackling environmental challenges.

The implementation of Priority 4 "Improving the efficiency of international ocean governance and creating preconditions for safety, security, cleanliness and sustainable management of the seas and oceans" meets basic needs for the development of the fisheries sector in the Republic of Bulgaria as a Black Sea coastal state.

The main objective of this contract is: Preparation of an independent strategic environmental assessment (SEA) for the purpose of programming the Maritime, Fisheries and Aquaculture Program 2021-2027 and, if necessary, following instructions from the competent environmental authority, preparation of Appropriate Assessment, according to Art. 4 of the Ordinance on the terms and conditions for assessment of the compatibility of plans, programs, projects and investment proposals with the subject and objectives of protection of protected areas, as part of the SEA Report.

Environmental assessment of plans and programs is a preventive tool for assessing possible significant environmental impacts resulting from the implementation of plans and programs at national, regional and local levels.

Its aim is to ensure a high level of environmental protection and that environmental considerations are taken into account in the preparation, adoption and implementation of plans and programs.

The environmental assessment subject to this contract shall be prepared at the same time as the preparation of the Maritime, Fisheries and Aquaculture Program 2021-2027, taking into account the objectives of the strategy, the territorial scope and the level of detail so as to identify and describe and appropriately assess the possible effects of the implementation and the Environmental Assessment Guidelines issued by the European Commission and the opinion of the EC Competent Authority.

The implementation of the current Contract includes the following activities:

1. Preparation of the necessary documents for notification, assessment of the need and scope for the SEA assessment and the Appropriate Assessment by the relevant Competent Authorities;
2. Preparation of draft on the SEA Report in accordance with the requirements of Art. 16 and Art. 17 form the SEA Ordinance, incl. Appropriate Assessment (if such had been required by the Competent Authority);
3. Assistance to the Contracting Authority in conducting consultations with the public, interested bodies and third parties who may be affected by the plan or program, in accordance with the requirements of Chapter Four of the SEA Ordinance;
4. Preparation of final version of the SEA Report.

# Analysis on the results and the achievements within the implementation of the contract

## Analysis of the results and the achievements within the implementation of Activity 1: „*Preparation of the necessary documents for notification, assessment of the need and scope for the SEA assessment and the Appropriate Assessment by the relevant Competent Authorities*“ from theContract

The results achieved within implementation of Activity 1 include:

* Introductory meeting with the Contracting Authority;
* Collected information and documents for the SEA Report;
* Prepared and agreed Scoping Report;
* Prepared written notification to the Competent Authority in accordance with Annex №3 of the SEA Ordinance;
* Prepared request for assessment of the need and scope of the SEA Report;
* Introductory report presented.

On 07.07.2021 an Introductory Meeting was held between the Contracting Authoriry, represented by the Maritime Affairs and Fisheries Directorate and the Contractor P-United Ltd. The meeting was attended by the Director of the Directorate, Head of the Programming Department of the Maritime Affairs and Fisheries Directorate, Chief Expert of the same department and the Manager of P-United Ltd.

During the meeting, the Contractor presented in detail the steps to be taken to carry out an Strategic environmental assessment (SEA) of the Maritime, Fisheries and Aquaculture Program (MFAP), outlining the timetable for the procedure. He also expressed concern that if at some stages of the SEA implementation procedure the competent authority (MoEW) did not meet the deadlines for the ruling or requested additional actions / information, this would lead to deviation from the submitted schedule and lead to its non-compliance. At the same time, the manager of P-United Ltd. declared that the company's team will prepare the necessary documents ahead of time, so that if there is a delay by the MoEW, it can be at least partially compensated. During the meeting a practical action plan was drawn up and the ways of communication and coordination between the Contracting Authority and the Contractor were specified.

The introductory meeting can be assessed as effective and productive.

Immediately after the official Contract start, the experts involved were mobilized and the necessary information and documents for the environmental assessment were collected.

The Contractor's team prepared a written notification in accordance with Annex № 3 of the SEA Ordinance and a written request in accordance with Annex № 4 of the SEA Ordinance. They were provided to the Contracting Authority, together with an Introductory Report on 08.07.2021. On the same date the prepared Scoping Report and the Scheme for consultations were submitted.

According to the Contract and the technical specification for the implementation of Stage 1, the Contractor has fulfilled its obligations on time.

## Analysis of the results and the achievements within the implementation of Activity 2: „*Preparation of draft on the SEA Report in accordance with the requirements of Art. 16 and Art. 17 form the SEA Ordinance, incl. Appropriate Assessment (if such had been required by the Competent Authority)*“ from the Contract

The implementation of Activity 2 leaded to the achievement of the following result:

* Submitted First intermediate Report, incl. draft of SEA Report, developed in accordance with the SEA Ordinance and if it is necessary – with the Ordinance on the Appropriate Assessment.

In implementation of Activity 2, a draft report on Strategic Environmental Assessment (SEA) was prepared, according to the requirements of Art. 16 and Art. 17 of the SEA Ordinance.

The strategic environmental assessment has been prepared in accordance with the regulatory requirements and according to the normatively determined content. For the preparation of the draft SEA report, all necessary studies and analyzes have been performed by the Contractor's team, and scientific information necessary for the issuance of an SEA opinion for coordination of the program has been collected.

The drafting of the SEA report used the guidelines and methodologies for strategic environmental assessment published on the European Commission's website https://ec.europa.eu/environment/eia/sea-support.htm and on the Ministry of environment and water's website, key topic Preventive activity / Environmental assessment / Guidelines for implementation - https://www.moew.government.bg/bg/prevantivna-dejnost/ekologichna-ocenka /.

At the time of drafting the SEA report, the Contracting Authority had not started the administrative implementation of the SEA procedure and accordingly the instructions on the applicable SEA procedure from the MoEW had not been received, nor had the required consultations on the Scoping Report started. In this regard, the draft SEA report was prepared on the basis of available information and documentation, in accordance with the relevant regulatory requirements set out in the SEA Regulation and applicable regulations, and the experience of the Contractor's team with similar projects, but this draft SEA Report did not comply with the instructions of the Ministry of Environment and Water for conducting the SEA procedure (due to the lack of such instructions at that time), nor did the draft SEA report reflect the views of stakeholders included in the consultation scheme from the consultations on the Scoping report (as such consultations were not carried out by the the Contracting Authority, respectively such opinions were not received and were not provided to the Contractor).

On 09.08.2021 with a letter with registration index № 70-3917 the Contractor submitted to the Contracting Authority the First Interim Report on the implementation of the Contract, accompanied by a draft SEA report and non-technical summary, committing to revise / supplement the draft SEA REport, after the letter / opinion received from the MoEW has been provided to him by the Contracting authority.

Given that the competent authority (MoEW) set additional conditions to the Scoping Report and / or the Scheme for consultations in its opinion on the submitted Notification (№ 04-00-2027 / 20.09.2021), on 27.09.2021 The Contractor has provided to the Contracting Authority:

o Updated Scoping Report;

o Updated Consultation Scheme.

With a handover protocol from 29.09.2021, the Contracting Authority accepts the work under Stage 2 of the Contract.

In order to overcome the discrepancies between the deadlines set in the technical specification / contract and the actual deadlines of the SEA procedure, it was necessary to extend the deadlines for implementation of the third and fourth stages and the deadline for overall implementation of the contract. In this regard, the Contracting Authority and the Contractor have signed the Supplementary Agreement № RD 51-67 / 28.10.2021 to the Contract № RD 51-67 / 28.06.2021.

## Analysis of the results and the achievements within the implementation of Activity 3: „*Assistance to the Contracting Authority in conducting consultations with the public, interested bodies and third parties who may be affected by the plan or program, in accordance with the requirements of Chapter Four of the SEA Ordinance*“ from the Contract

The implementation of Activity 3 is expressed in the achievement of the following results:

• Conducted consultations with stakeholders and public discussion;

• Presented second interim report containing information on the conducted consultations / public discussion and updated draft SEA report.

For the purposes of the implementation of the activity, and also in connection with the reflection of the opinions received in the course of the consultations under the Scoping Report, on 06.12.2021 with a letter with registration № 70-5763 the Contractor provided to the Contracting Authority:

• Updated Strategic Environmental Assessment Report of the MFAP 2021-2027;

• Instructions for conducting consultations according to the SEA Ordinance;

• Notice of consultations;

• Templates of cover letters for the purposes of disseminating the Notice for consultations to the competent body of the Ministry of Environment and Water and to the interested parties.

According to Art. 20, para. 3 of the SEA Ordinance, the Contracting Authority shall hold consultations on the SEA report and with the competent authority (Ministry of Environment and Water, MoEW), providing it with the documentation on paper and electronic media for an opinion within the period under para. 1, item 1, letter c) of the SEA Ordinance (.ie "not shorter than 30 days").

For the purpose of preparing the Second Interim Report and reflecting the opinions received during the consultations on the SEA report, the Contractor requested from the Contracting Authority the opinions received during the procedure and outgoing numbers of cover letters by which the Notice for consultations was sent to interested parties.

From the accompanying letters provided by the Contracting Authoriry, it can be seen that with ref. № 0403140 / 07.01.22 the Ministry of Agriculture has provided the MoEW with the documentation for conducting SEA consultations, together with the Notice for conducting consultations. Thus, the Contracting Authority has given the Competent Authority a period of 6 (six) days to express an opinion that contradicts the requirements of the SEA Ordinance.

At the same time, according to Art. 20, para. 3, item 1 of the SEA Ordinance, the MoEW requires an opinion on the documentation from the competent authority under Art. 13, para. 1 - Ministry of Health, setting a deadline for response of up to 20 days. At its discretion, it shall request an opinion on the documentation from other competent bodies or organizations, setting a term of up to 14 days (Art. 20, para. 3, item 1). According to Art. 20, para. 3, item 3, the MoEW reflects the received opinions in the answer to the Contracting Authority. In practice, the competent body of the Ministry of Environment and Water was made unable to fulfill this obligation by 13.01.2022, when it was notified and received the necessary documentation on 07.01.2022.

All other interested institutions included in the Consultation Scheme also received the Notice for consultations dated 07.01.2022, with a deadline for expressing opinions and recommendations until 13.01.2022.

All this could compromise the procedure for environmental assessment of the draft MFAP2021-2027.

In view of the above, the Contracting Authority notified the Contractor by e-mail on 14.01.2022 that it extended the term for consultations until 21.02.2022, canceled the scheduled public hearing and announced a new date for public discussion - 09.03.2022.

In order to comply with its commitments under the Contract, on 19.01.2022 with registration index 70-317 the Contractor has provided the Contracting Authority:

* Second Interim Contract, incl. information of the conducted consultations/ public hearing;
* Updated draft of the SEA Report on MFAP 2021-2027 (*at the time of preparation of the second interim report, only 4 opinions have been received on the Environmental Assessment Report, which did not contain comments and / or recommendations*);
* Non-technical summary to the SEA Report;

With a handover protocol from 24.01.2022, the Contracting Authority accepts the implementation of Stage 3, noting that the SEA Report does not reflect the opinions of the competent authority for environmental assessment of plans and programs - Ministry of Environment and Water (MoEW), as well as the Ministry of Health, Regional Inspectorates of Environment and Water and Basin Directorates, due to the fact that they have not yet been received in the Ministry of Agriculture.

Obtaining and reflecting the opinions of the competent institutions is a mandatory element of the SEA procedure, otherwise there is a risk of compromising it. In this regard, the Ministry of Agriculture has extended the deadline for consultations and has set a new date for public discussion of the SEA Report. All opinions that will be received within this extended period and / or during the public discussion should be reflected in the SEA Report.

The Contractor has correctly indicated this circumstance in the second interim report and undertakes to revise / supplement the draft of SEA Report after providing it with the opinions received from the Contracting Authority from the MoEW, MH, RIEW, BD and others in view of the received comments and recommendations in the Ministry of Agriculture.

In connection with the above, the Contracting Authority and the Contractor have signed a Supplementary Agreement RD 51-67 / 11.02.2022 to Contract № RD 51-67 / 28.06.2022, which extends the term of performance of the service and the term of performance of Stage 4.

## Analysis of the results and the achievements within the implementation of Activity 4: „Preparation of final version of the SEA Report“ from the Contract

The implementation of Activity 4 is expressed in the achievement of the following result:

* Submitted and accepted final report on the service, containing a final Report on Strategic Environmental Assessment, summary, monitoring and control measures and a proposal for their implementation.

The opinions, comments and recommendations received as a result of the consultations do not lead to the development of a new version of the program, nor are they related to additional negative impacts on the environment and human health. Following consultations with the responsible institutions and the public, the SEA Report was supplemented by the views and opinions expressed during the consultations, which are insignificant for the SEA as a whole and do not concern the assessment methodology, impact assessment or the SEA conclusions.

In the opinion of the Ministry of Environment and Water with ref. № 04-00-2027 / 17.03.2022, in connection with the consultations on SEA Report, measures for monitoring and control of the impact on the environment and human health during the programme impleentation are proposed. The Contracting Authority did not agree with some of the proposed measures for monitoring and control and the Contractor helped him to prepare an objection to them, which was submitted to the MoEW (ex. № 0403-18 / 31.03.2022) within the normatively set deadline.

After the public discussion of the draft MFAP 2021-2027 and the SEA Report, the opinions received during the SEA consultations were reflected in the SEA Report and on 29.04.2022 with registration index 70-2309 the Contractor provided to the Contracting Authority:

* Supplemented SEA Report, incl. Annexes and Non-Technical Summary, in accordance with the opinions received at the Ministry of Agriculture as well as the comments received during the public hearing.

On the same date (29.04.2022) with registration index 70-2310 the Contractor provided to the Contracting Authority:

* Completed Request for issuance of an opinion on environmental assessment by the competent body of the Ministry of Environment and Water, containing the final version of the Environmental Assessment Report of the MFAP2021-2027.

As a result of the environmental assessment of the draft MFAP 2021 - 2027, based on the results of the analysis and assessment of the potential impacts of the envisaged priorities, specific objectives and planned activities, the team of independent experts concluded that the implementation of the program does not significant negative impact on the environment and human health, and the implementation of the measures recommended in item 7 of the SEA Report will limit and prevent the projected negative impacts and will increase the degree of environmental impact of the program.

At the time of submission of this Final Report, the following is forthcoming (for reasons beyond the Contractor's control):

o Issuance of an SEA Opinion by the Minister of Environment and Water;

o Preparation of a summary report under Art. 29, para. 1 of the SEA Ordinance on the manner of reflecting the SEA results in the draft MFAP2021-2027 and submission by the Contracting Authority to the competent environmental authority for ruling.

o Ensuring public access to the summary report after the positive decision of the competent authority on it.

# In-depth analysis of the problems and recommendations for their solution in the future

The First and Second Interim Reports under this current Contract present the difficulties and problems that have arisen for the respective reporting period in the process of developing the draft Strategic Environmental Assessment Report of the MFAP 2021-2027, and they are mainly related to the extremely short deadlines for implementation of the Contract, which do not correspond to the real terms and requirements for sequence of stages in the implementation of the SEA procedure and the development of FMAP 2021-2027.

For the period of the Contract, it was necessary to extend the term of performance twice, for reasons independent of the Contractor, as follows:

***Supplementary agreement № RD 51-67 / 28.10.2021 to Contract № RD 51-67 / 28.06.2021 for extension of the term for performance of the service - instead of 130 days from the date of concluding a contract for performance - 260 days from the date of concluding the performance contract***

The extension of the term for performance of the service was necessary due to the impossibility to observe the term for performance up to Stage 3: "Conducting consultations and public discussion", which is 75 calendar days from concluding a Contract with the Contractor, which is **11.09.2021**.

*The specified term also includes the time for ruling of the competent body - MoEW - 1. 14 days under the Notification for the program; 2. The time for ruling on the Scheme for conducting consultations on SEA and the Scoping Report; 3. The time for conducting consultations on the SEA Report (30 days) and conducting a public discussion.*

**Chronology:**

The Contractor P-United Ltd. has prepared a Notification in accordance with Annex № 3 of the SEA Ordinance and submitted it to the Contracting Authority on 08.07.2021.

The Contracting Authority submitted to the MoEW the Notification on 23.07.2021.

By letter dated 20.09.2021, the Ministry of Environment and Water ruled on the applicable procedure in connection with the SEA Ordinance, giving instructions on the next steps to be taken by the Contracting Authority, resp. the SEA Contractor. 1) Scheme for consulting the public, interested bodies and third parties who are likely to be affected by the implementation of the program (Scheme) and 2) Scoping Report, and consultations should be held on the prepared Scoping Report.

The Contractor has provided the Contracting Authority with the Scheme and the Scoping Report, together with the Notification on 08.07.2021.

In connection with the recommendations from the opinion received from the Ministry of Environment and Water (dated 20.09.2021) on 27.09.2021, the Contractor has provided updated Consulting Scheme and Scoping Report to the Contracting Authority.

The updated Consulting Scheme and Scoping Report were submitted to the Ministry of Environment and Water by the Contracting Authority on 07.10.2021, and the deadline for consultations on the Scoping Report has been set until 20.10.2021.

The competent body of the Ministry of Environment and Water shall rule on them with an Opinion dated 26.11.2021.

***Supplementary agreement № RD 51-67 / 11.02.2022 to Contract № RD 51-67 / 28.06.2021 for extension of the term for performance of the service - instead of 130 days from the date of concluding a contract for performance - 390 days from the date of concluding the performance contract***

The extension of the term for execution of the service was necessary due to the impossibility to observe the term for execution of Stage 3: "Conducting consultations and public discussions", which is not later than 205 calendar days from the conclusion of the Contract with the Contractor, which is **19.01.2022.**

*The specified term includes the time for conducting consultations on the SEA Report (30 days) and conducting a public discussion.*

**Chronology:**

The Contractor P-United Ltd. submitted to the Contracting Authority on **06.12.2021** an updated environmental assessment report, instructions for conducting consultations and a Notice for conducting consultations with a deadline for conducting consultations until **13.01.2022.**

The Contracting Authority published the Notice for conducting the consultations and the documentation on the SEA on the internet address: https://www.eufunds.bg/bg, on **10.12.2021.**

On January 11, 2022, the Contractor requested the Contracting Authority to provide him with ent. the number of letters sent to interested parties for consultations and the opinions received during the consultations, with a view to reflecting them in the SEA Report.

From the accompanying letters provided by the Contracting Authority on 11.01.2022, it can be seen that with ref. **№ 0403140 / 07.01.22**. The Ministry of Agriculture has provided the MoEW with the documentation for conducting SEA consultations, together with the Notification for conducting consultations. Thus, the Contracting Authority has given the Competent Authority a period of 6 (six) days to express an opinion that contradicts the requirements of the SEA Ordinance and violates the SEA procedure.

On **14.01.2022** by e-mail the Contracting Authority notifies the Contractor and all interested parties that it extends the term for consultations on the Strategic Environmental Assessment Report to **21.02.2022** and sets a date for public discussion **09.03.2022**.

In order to solve such problems in the future, the processes of developing the respective plan / program should be coordinated with the stages of the environmental assessment procedure. The deadlines for holding consultations under the Scoping Report, a minimum of 30 days for consultations on the SEA Report, holding a public hearing (if required), as well as these deadlines, as well as the statutory deadlines for the competent authority to rule, must be taken into account and should not be included in the total time for the implementation of the service.

# Deviations and/ or problems during the current reporting period

On 29.04.2022 with registration index 70-2310 the Contractor submitted to the Contracting Authority a Complete Request for issuance of an opinion on strategic environmental assessment by the competent body of the Ministry of Environment and Water, containing a final version of the Strategic Environmental Assessment Report of MFAP 2021-2027.

As of 14.06.2022, the Contracting Authority has not taken action to submit the package of documents for issuing an opinion on strategic environmental assessment to the MoEW. The statutory deadline for issuing an SEA opinion is 30 days from the submission of the Request (Article 25 of the SEA Ordinance). As the practice and experience of the Contractor give grounds to assume the possibility of overdue of this period by the competent authority.

In view of this, the Contractor is unable to prepare a proposal to reflect the opinion on the strategic environmental assessment as of the date of preparation of this Final Report.

# Main Achievements

The main achievement of the implementation of the current Contract is the Report on Strategic Environmental Assessment of the draft Maritime, Fisheries and Aquaculture Programme 2021-2027, supplemented by the results of consultations and public discussion.

The conclusion of the team of independent experts is that the implementation of the program does not imply a significant negative impact on the environment and human health.

The Contractor has provided the Contracting Authority with all necessary documents for starting the procedure for issuing a Strategic Environmental Assessment Opinion by the competent authority - the Ministry of Environment and Water.

# Deliverables in accordance with the Technical specification

Final report on the service, containing a final Report on Strategic Environmental Assessment, a summary, monitoring and control measures and a proposal for their implementation.

The final Report on Strategic Environmental Assessment, summary, monitoring and control measures and a proposal for their implementation was submitted to the Contracting Authority on 29.04.2022 with registration index 70-2310.